TERMS OF REFERENCE (TOR) ON ISSAI IMPLEMENTATION PROGRAMME

Sub Project: Establishment of ISSAI Facilitators’ Pool

for ASEANSAI Members

- Background

- During INCOSAI XX in South Africa in 2010, the International Standards of Supreme Audit Institutions (ISSAIs) were approved to be used by all SAIs as the main references in performing their public sector auditing mandate and function.  Ever since, the Professional Standard Committtee (PSC) together with the INTOSAI Development Initiatives (IDI) and the support from donors rolled out the initiative to SAIs for adoption and implementation in the respective SAIs through the ISSAIs Initiative Implementation Program or the 3i Program.

- As a follow up of the regional program, ASOSAI in February 2013 in Phnom Penh, Cambodia, 20 members SAIs of ASOSAI signed a commitment to promote the implementation of ISSAIs in each participating SAI. Eight out of the 20 SAIs were members of ASEANSAI and had started to implement the commitment of adopting ISSAIs as reference and audit guidance in their respective SAIs.

- The effort of adopting the international standard is in line with the goals of ASEANSAI to develop capacity building of member SAIs as outlined in the ASEANSAI Strategic Plan.  The 2014 Work Plan of the Knowledge Sharing Committee has mapped out activities to promote ISSAI implementation in ASEANSAI members by carrying out a research on ISSAI implementation for level 1 & 2 as well as level 3 & 4 simultaneously.

- There have been series of trainings held by INTOSAI-IDI cooperation or ASOSAI-IDI to promote competency of ISSAI Facilitators who have helped the facilitation of ISSAI implementation roll out at the regional level and SAIs. However, as to date a pool of ISSAI facilitators is still not established which could enable the trained facilitators to be managed according to their expertise and facilitate the implementation of ISSAI.

- One of the expected outcomes from 3i Program by INTOSAI is the creation of a pool consisting of at least 180 ISSAI facilitators for financial, performance and compliance auditing in the five English speaking regions of INTOSAI. Based on this scenario, creation of ISSAI facilitators’ pool in the ASEANSAI region is considered an important initiative.

- Purposes

The Knowledge Sharing Committee’s intentions to create the ASEANSAI ISSAI facilitators’ pool are to:

- Provide expertise for ISSAI facilitation activities for financial, performance and compliance audits;

- Increase the pool of ISSAI facilitators in ASEANSAI through training and workshop using the IDI training materials;

- Enhance sharing of information, best practices and expertise through the online exchange platforms, databases, etc.;

- Facilitate process  of adoption of ISSAIs for a more effective implementation;

- Increase auditor’s skills in the use of ISSAIs as the auditing standards; and

- To achieve a better understanding of each requirements of ISSAI standards

- Form of Activities

To achieve the desired objectives, the following activities will be carried out:

- Coordinate activities with the project leader of ISSAI Implementation (SAI Philippines);

- Establish cooperation and coordination with INTOSAI IDI and PSC for possible assistance on the establishment of curriculum, modules, methods, experts, and trainers;

- Create database through effective communication with CBC of INTOSAI subcommittee to manage the INTOSAI experts’ database data collection of the current ISSAI facilitators within the ASEANSAI region;

- Conduct needs assessment survey to all ASEANSAI members on their needs for specific ISSAI facilitation;

- Conduct trainings for ISSAI Facilitators;

- Coaching/ Sharing expert; and

- After the establishment of the ISSAI facilitators pool, the following activities are planned :

- Management of the facilitators

- Arrangement of ISSAI facilitation; involving ISSAI facilitators on piloting audit or related activities of ISSAI Implementation Project

- Maintenance, improvement and quality control of the ISSAI facilitation activities

- Database update and maintenance.

- Scope

- The scopes of creating database are: (i) identification of current state of ISSAI facilitators in the region; (ii) data collection of the current ISSAI facilitators from internal and external ASEANSAI; (iii) establish an effective database of the current ISSAI facilitators.

- The scopes of conducting needs assessment survey are: (i) identification of each of ASEANSAI members’ mandates and (ii) the level of ISSAI implementation in each SAI.

- The scopes of consolidating the ISSAI facilitators are meetings with secretariat and ISSAI facilitators to have common perception on the ISSAI implementation.

- The scopes of increasing the pool of ISSAI facilitators are: (i) Training of Trainers using the IDI training materials and (ii) focus group discussion/workshop.

- The scopes of operational of the ISSAI pool are: (i) management of the facilitators (include planning, evaluation and quality control); (ii) arrangement of ISSAI facilitation; (iii) update and maintain database; (iv) maintain good communication with KSC and other subcommittees, Secretariat, and PSC INTOSAI.

- Participants

- Sub Project Leader: Malaysia

- ISSAI Facilitators (IDI Certified Facilitators)

- ISSAI Experts from IDI and PSC INTOSAI

- ISSAI Trainees

- Donor: ???

- Proposed Timeline

| No | Activities | Proposed timeline |
| --- | --- | --- |
| 1. | Approval of the Proposal | 8 February 2015 |
| 2. | Creation of Database | March 2015 |
| 3. | Needs Assessment Survey | End of March 2015 |
| 4. | ISSAI Facilitator Consolidation | Early May 2015 |
| 5. | Training of Trainers | End of June 2015 |
| 6. | FGD/Workshop | August 2015 |
| 7. | Monitoring and Evaluation | September 2015 |
| 8. | Maintenance of ISSAI Facilitator Pool Database | March – December 2015 |

- Expected Results

- A pool of ISSAI facilitators for financial, performance and compliance audit within ASEAN region;

- A well managed pool of ISSAI facilitators which could fulfill the needs of SAIs within the ASEAN region; and

- A well implemented and effective adoption of ISSAI which could lead to better performance of SAIs through high quality audits.

- Budget and Source of Fund

The proposed budget is as follow:

| No | Activities | Proposed budget | Total | Source of fund |
| --- | --- | --- | --- | --- |
| 1. | Approval of the proposal |  |  |  |
| 2. | Creation of Database and Needs Assessment |  |  |  |
| 3. | ISSAI Facilitator Consolidation (3 days) - Meeting Venue – Package for Participants (25 person) and Secretariat (5 persons) |  |  |  |
| 4. | Training, Workshop and FGD Training of Trainers (3 days) - Meeting Venue – Package for Participants (25 person) and Secretariat (5 persons) FGD/Workshop (5 days) - Meeting Venue – Package for Facilitators and Trainees (30 person) and Secretariat (5 persons) |  |  |  |
| 5. | Monitoring and Evaluation |  |  |  |
| 6. | Maintenance of ISSAI Facilitator Pool Database |  |  |  |
|  | Total Proposed Budget |  | USD ….. |  |