## Slide 1: ISSAI Implementation
By SAI- Philippines as Project Leader
Luz L. Tolentino
Assistant Commissioner
Professional and Institutional Development Sector
Commission on Audit

## Slide 2: KSC on ISSAI Implementation
Date | Location/ Venue | Output
29-30 May 2014 | Kuala Lumpur, Malaysia | Agreements
Capacitating SAIs on ISSAIs will be on staggered basis starting with FA ISSAIs.
FA ISSAI implementation will start with a set of 15 ISSAIs as baseline
Workshop outputs will be monitored by Project Leader

## Slide 3: KSC on ISSAI Implementation
Date | Location/ Venue | Output
18-22 August 2014 | Bandung, Indonesia | Challenges and Solutions, Propositions for support on ISSAI implementation through ASEANSAI

## Slide 4: Propositions for support on ISSAI implementation
Raising Awareness of AGs on ISSAI
Ensure continuity of working on ISSAI implementation
Improving quality control and quality assurance
Developing audit program (connect risk to audit procedures)
Internal controls (IT system); evaluation and risk assessment process

## Slide 5: Propositions for support on ISSAI implementation
Resistance of auditors to change
Developing sampling techniques
Better understanding on risk-based approach in relation to ISSAI 1315 and 1330.

## Slide 6: KSC on ISSAI Implementation
Date | Location/ Venue | Output
30-31 October 2014 | Manila, Philippines | Action Plan

## Slide 7: ISSAI Implementation Action Plan
Activities | Responsibility | Timeline
Training on internal control systems, as one of the core content topics from the 5 ISSAIs | Sub-Project Leader (SAI Thailand) in coordination with Training Committee Chair (SAI Philippines) | Instructors’ Design Meeting: End of February 2015 Training: May 2015
Follow up activities on the learning from the Training on internal control using trained ISSAI Facilitators from the Created Pool | Sub-Project Leader (SAI Thailand) in coordination with TC Chair | September 2015

## Slide 8: ISSAI Implementation Action Plan
Activities | Responsibility | Timeline
Training on risk- based audit, as one of the core content topics from the 5 ISSAIs (including materiality) | Sub-Project Leader (SAI Indonesia) in coordination with Training Committee Chair (SAI Philippines) | Instructors’ Design Meeting: June 2015 Training: October 2015
Follow up activities on the learning from the Training on risk-based audit approach using trained ISSAI Facilitators from the Created Pool | Sub-Project Leader (SAI Indonesia) in coordination with TC Chair | March 2016

## Slide 9: ISSAI Implementation Action Plan
Activities | Responsibility | Timeline
Increase the pool of ISSAI Facilitators in ASEANSAI | Sub-Project Leader (SAI- Malaysia) | 

## Slide 10: ISSAI Implementation Action Plan
Activities | Responsibility | Timeline
Prepare questionnaire to assess progress since Bandung I on the 5 ISSAIs discussed in Bandung (1210, 1300, 1315, 1320, 1330) and better understand training needs | Project Leader (SAI Philippines) | January- February 2015
Bandung II, assess progress towards 5 ISSAIs and start working on the next cluster of ISSAIs | Project Leader (SAI Philippines) | Early December 2015

## Slide 11: ISSAI Implementation Action Plan
Activities | Responsibility | Timeline
Prepare Statement of Commitments to engage Heads of SAIs- ASEANSAI members Importance of ISSAI implementation Key results of the Bandung Workshop | Project Leader (SAI Philippines) and KSC Chair- SAI Malaysia ASEANSAI Secretariat | January 2015 For circulation: Starting February 2015 Official signing by SAI Heads of ASEANSAI by November 2015 (tentative)

## Slide 12: Expected Results in Workshops on ISSAI Implementation
A high level of commitment from ASEANSAI members to achieve quality audit
A sustained effort to maintain professional and quality audit in compliance with ISSAI
A more effective adoption / implementation process by committed SAIs

## Slide 13: SAI Proposed Commitments
Sustain all initiatives and efforts on adopting the ISSAIs in line with the goals of ASEANSAI
Support all endeavors and activities of the KSC which mapped out activities that promote ISSAI implementation among ASEANSAI members, through workshops, surveys and focus group discussions on ISSAI implementation and all the related trainings and capacity building activities

## Slide 14: SAI Proposed Commitments
Support and authorize the SAI’s ISSAI facilitators and those involved in ISSAI implementation
To share templates and experiences with other SAIs through different channels
(e.g. in meetings and email groups)
To monitor and evaluate ISSAI implementation annually

## Slide 15: SAI Proposed Commitments
Reserve the facilitators for facilitating ISSAI interventions at SAI and ASEANSAI levels
Actively cooperate in all international undertakings and support each other for the common good of ASEANSAI

## Slide 16: Implementation of ISSAIs is …
… the primary responsibility of
Supreme Audit Institutions.